## Error Register
Record ID | Source System | Platform | Repo or Project | Error / Issue | Root Cause | Fix / Recommended Fix | Contingency / Fallback | Evidence | Status | Last Seen | Source URL
ERR-001 | GitHub | Vercel / Build | espacios-me/web | Install failure from Vite 7 peer dependency conflict | @builder.io/vite-plugin-jsx-loc@0.1.1 advertises a Vite 4/5 peer range while the repo is already on Vite 7, so default npm install fails before the build starts. | Add a root .npmrc with legacy-peer-deps=true so install can complete for current deploys. | Long-term: remove or replace the Builder plugin if unused, or standardize the intended installer path such as pnpm install --no-frozen-lockfile and align package versions. | PR #17 states recent PR deploys were blocked before build due to dependency resolution failure and proposes adding .npmrc. | Open / fix proposed | 2026-03-25 | https://github.com/espacios-me/web/pull/17
ERR-002 | GitHub | Cloudflare / Vercel config drift | espacios-me/web | Cloudflare deployment error tied to VITE_APP_ID reference and leftover Vercel config | The frontend referenced VITE_APP_ID and the repo still contained Vercel-specific config, creating deployment drift while moving to Cloudflare. | Default VITE_APP_ID to an empty string in code and remove vercel.json from the repo. | Add prebuild environment validation and keep platform-specific config isolated so Cloudflare deploys do not inherit dead Vercel settings. | PR #8 says it fixes the Cloudflare deployment error by removing VITE_APP_ID and cleaning up Vercel leftovers; patch shows both changes. | Partially addressed | 2026-03-24 | https://github.com/espacios-me/web/pull/8
ERR-003 | GitHub | Env / Deployment settings | espacios-me/web | Repeated VITE_APP_ID / vite_app_id environment mismatch noise | Even after the repo-side blocker was identified, deployment comments still referenced a stale VITE_APP_ID / vite_app_id mismatch in settings. | Clean the deployment platform environment settings so dead variable references are removed instead of merely tolerated. | Maintain one canonical env manifest per platform and compare it against code references in CI. | PR #17 notes the repeated GitHub bot comment about VITE_APP_ID / vite_app_id may still need cleanup in Vercel project settings. | Open / cleanup needed | 2026-03-25 | https://github.com/espacios-me/web/pull/17
ERR-004 | GitHub | Analytics / Frontend config | espacios-me/web | Hardcoded analytics placeholders in HTML made builds and deployments brittle | client/index.html embedded %VITE_ANALYTICS_ENDPOINT% and %VITE_ANALYTICS_WEBSITE_ID% placeholders directly, making build behavior sensitive to env wiring. | Move analytics injection to runtime in main.tsx and no-op when analytics env vars are missing. | Keep analytics disabled by default outside production and let CI warn only when production expects analytics. | PR #15 removes hardcoded analytics tags from HTML and injects analytics at runtime only when vars are present. | Addressed in PR | 2026-03-25 | https://github.com/espacios-me/web/pull/15
ERR-005 | GitHub | TypeScript / CI | espacios-me/web | TS5101 deprecation warning (baseUrl) caused typecheck noise or failure | pnpm check hit an existing tsconfig deprecation warning related to baseUrl under newer TypeScript behavior. | Short-term: add ignoreDeprecations: "6.0" so CI can pass while config cleanup is pending. | Properly modernize tsconfig instead of suppressing the warning forever; pin TS behavior in CI until that cleanup is done. | PR #15 says pnpm check failed because of TS5101, and PR #8 patch adds ignoreDeprecations: 6.0. | Mitigated, not fully cleaned up | 2026-03-25 | https://github.com/espacios-me/web/pull/15
ERR-006 | GitHub | Cloudflare Wrangler / CI | espacios-me/web | Ambiguous Wrangler environment targeting in CI deploys | Deploy commands were not explicit enough about the target Wrangler environment, so uploads could land in the wrong place or create ambiguity. | Use explicit deploy commands such as npx wrangler versions upload --env=production or --env=staging. | Keep branch-to-env mapping in one source of truth and enforce it in the workflow so main, develop, and tags cannot drift. | PR #12 documents explicit --env usage and the branch/tag to environment mapping. | Addressed by documentation; enforce in CI | 2026-03-25 | https://github.com/espacios-me/web/pull/12
ERR-007 | GitHub | Cloudflare Wrangler | espacios-me/web | Wrangler project name mismatch versus CI expected project name | wrangler.toml naming did not align with the name used in CI/deploy logs, causing overrides and warning churn. | Rename the top-level worker to web and align env names to web-production and web-staging. | Add a CI assertion that checks wrangler.toml naming against the expected deployment target before deploy runs. | PR #13 updates wrangler.toml naming to match the CI expected project. | Addressed in PR | 2026-03-25 | https://github.com/espacios-me/web/pull/13
ERR-008 | GitHub | Cloudflare Pages / Wrangler | espacios-me/web | Mixed Cloudflare Pages configuration and Wrangler asset-upload model | The repo was transitioning from Pages-specific configuration to Wrangler static asset uploads, leaving two deployment models in play. | Use Wrangler [assets] with the built static directory and remove obsolete Pages-specific config blocks. | Choose one deployment model only — either Cloudflare Pages or Worker/Wrangler asset upload — and keep docs plus CI aligned to it. | PR #10 moves away from Pages-specific settings to Wrangler assets upload and removes Pages-specific config. | Transition in progress / needs standardization | 2026-03-24 | https://github.com/espacios-me/web/pull/10
ERR-009 | GitHub | GitHub Actions / Cloudflare | espacios-me/web | Deploy workflow depends on Cloudflare secrets that can fail silently if missing | The GitHub Actions review-and-deploy workflow requires CLOUDFLARE_API_TOKEN and CLOUDFLARE_ACCOUNT_ID, but missing secrets would break deploys. | Ensure both required secrets are present in GitHub Actions before deployment jobs run. | Add a preflight secrets-check job that exits early with a human-readable error instead of failing deep in deployment. | PR #11 documents the workflow and required Cloudflare secrets. | Control item / verify in repo settings | 2026-03-25 | https://github.com/espacios-me/web/pull/11
Note on E2: Source: GitHub PR #17 in espacios-me/web.
Note on E3: Source: GitHub PR #8 and its patch in espacios-me/web.
Note on E4: Source: GitHub PR #17 in espacios-me/web.
Note on E5: Source: GitHub PR #15 in espacios-me/web.
Note on E6: Source: GitHub PR #15 and PR #8 patch in espacios-me/web.
Note on E7: Source: GitHub PR #12 in espacios-me/web.
Note on E8: Source: GitHub PR #13 in espacios-me/web.
Note on E9: Source: GitHub PR #10 in espacios-me/web.
Note on E10: Source: GitHub PR #11 in espacios-me/web.

## Summary
Deployment Error Register Summary
Generated | 2026-03-25
Total distinct error rows | 9
Source systems represented | GitHub
Count by platform |  | Count by status
Vercel / Build | 1 | Open / fix proposed | 1
Cloudflare / Vercel config drift | 1 | Partially addressed | 1
Env / Deployment settings | 1 | Open / cleanup needed | 1
Analytics / Frontend config | 1 | Addressed in PR | 2
TypeScript / CI | 1 | Mitigated, not fully cleaned up | 1
Cloudflare Wrangler / CI | 1 | Addressed by documentation; enforce in CI | 1
Cloudflare Wrangler | 1 | Transition in progress / needs standardization | 1
Cloudflare Pages / Wrangler | 1 | Control item / verify in repo settings | 1
GitHub Actions / Cloudflare | 1

## Notes
Scope and source notes
Included sources
GitHub PRs/issues already surfaced in this conversation
Linear was checked for related deployment context, but it did not add concrete error rows beyond project context.
Included topics
Cloudflare / Wrangler, GitHub Actions, Vercel config drift, env mismatches, analytics placeholders, TypeScript CI warnings.
Deduping rule
Multiple PRs about the same underlying issue were collapsed into one row where possible.
Not included
Frontend-only legal URL and Atom branding changes were excluded unless they affected deployment reliability.